## Planning Madagascar
Modèle de planification d'activité GoTeach - 2023
| Nom du pays: | Madagascar
| Nom du partenaire : | Partenaire SOS
| Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
ANTSIRABE | Introduction to employability | Explorer | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | Yes | Face 2 Face | Activity 1, 2, 3 | April 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 829.8
ANTSIRABE | Company discovery | Expose | Workplace visit | Visit to a local site or office (a few hours) to learn about different workplaces where employees perform tasks, jobs and projects, including a question-and-answer session with employees of the companies being visited. "Initiation of the Professional Workplace, including interest" | Labour Market orientation | Yes | Face 2 Face | Activity 1, 2, 3 | May 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 360.96
ANTSIRABE | How to write a CV and succeed in an interview. | Explorer | CV writing & interview skills training | Help youth create a powerful resume and learn how to prepare for an interview Understanding of the different methods of searching for job vacancies and how to apply resume and application letter writing skills and attend a job interview | Job hunting skills, technical skills | Yes | Face 2 Face | Activity 1, 2, 3 | May 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 385.38
Fort-Dauphin | Introduction to employability | Explorer | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | OUI | Présentiel | Activity 1, 2, 3 | April 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 705.56
Fort-Dauphin | Company discovery | Expose | Workplace visit | Visit to a local site or office (a few hours) to learn about different workplaces where employees perform tasks, jobs and projects, including a question-and-answer session with employees of the companies being visited. "Initiation of the Professional Workplace, including interest" | Labour Market orientation | OUI | Présentiel | Activity 1, 2, 3 | May 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 305.56
Fort-Dauphin | Know how to practice | Explore/Expose | Career talk / logistic-related training | Give young people an opportunity to discover promising professions according to their vision and choice Stimulate the creative spirit of young people through a presentation of professions by DHL volunteers on communication, IT and logistics. Not only will young people benefit from knowledge of the trades, but they will also discover the different production units in the sectors. | Labour Market orientation | OUI | Présentiel | Activity 1, 2, 3 | May 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 407.78
Boeny | Company and career discovery | Exposer | Company visit, career talk | Virtual visit of the workplace, meeting with staff by videoconference "Development of knowledge on educational and vocational guidance. Knowledge of the business world Knowledge of existing professions in the transport and logistics environment " | Labour market orientation | Yes | Virtual | 1,2,3 | 2023-07-01 | young people | 100 | 15 | SOS, Express | 422.2
Boeny | Professional meeting | Exposer | career talk | "Meeting with trade professionals to exchange and discuss their professional career on a trade (testimonial, sharing, success, etc.) and produce a catalog of existing professions at DHL Improve the career choice of young people according to their skills and talents. Young people have benchmarks in relation to their choice of orientation. Reinforced young people's understanding of the personal requirements of the world of professionalization With the catalog, young people develop skills in the concept of transport (air freight, rail, sea, etc.) and logistics | Labour market orientation | yes | Face 2 face | 1,2,3 | 2023-07-01 | young people | 100 | 1 | SOS, Express | 360.2
Boeny | How to write a CV and succeed in an interview, professionalisation | Explorer | CV writing & interview skills training | Employee training kit with DHL: CV development, cover letter, job application, interview "Young people master the conditions acquired upon hiring (CV writing, cover letter, attitude to the interview, etc.)" | Job hunting skills | yes | Face 2 face | 1,2,3 | 2023-07-01 | young people | 100 | 1 | SOS, Express | 452.2
Analamanga | Activity 1: Career discovery, career talk | Expose | Career talk | Choice of professions/ choose the professions and train the participants by professional speakers (school and professional testimony/ choice of institutes/ duration and diplomas/ job market | Labour market orientation | Yes | Face 2 face | Activité 1,3,4 | April 2023 | Young people | 50 | 20 | SOS, Express | 591.11
Analamanga | Activity 2: Professional mentoring | Explore | Mentoring | Assist the program participant in developing the skills and attitudes necessary to progress to employment, training or further education | perosnal maturity, labour maket orientation | No | Face 2 face | Activité 1,2,3,4 | June - November 2023 | Young people | 10 | 32 | SOS, Express | 48
Analamanga | Introduction to employability | Explorer | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | No | Face 2 face | Activité 1,3,4 | April 2023 | Young people | 50 | 20 | SOS, Express | 444.44
Analamanga | How to write a CV and succeed in an interview. | Explorer | CV writing & interview skills training | Help youth create a powerful resume and learn how to prepare for an interview Understanding of the different methods of searching for job vacancies and how to apply resume and application letter writing skills and attend a job interview | Job hunting skills, technical skills | No | Face 2 face | Activité 1,3, 4 | April 2023 | Young people | 50 | 20 | SOS, Express | 444.44
Analamanga | Internship in the retail department | Practice | Internship | Young people are doing their internship at the retail department for learning about sales and communication skills while supporting the retail team | Work experience | yes | Face 2 face | Activité 1,3, 4, 5 | April 2023 - June 2023 | Young people | 1 | 2 | SOS, Express | 133.1942
Analamanga | Job-shadowing retail department | Explore | Job-shadowing | Young people will learn the job as sales form the retail deparment during a week | Work experience | yes | Face 2 face | Activité 1,3, 4, 6 | April 2023 - June 2023 | Young people | 4 | 2 | SOS, Express | 44.3981
Atsinanana | Career discovery and employability training | Explore / Expose | Career fair and CV writing & interview skills training | Organize a day of orientation and training kits jobs Invite DHL, schools and professional institutions to present their available offers to the youth of SOS Village. To allow the youth to have ideas of orientation, to know the possibilities of course in Tamatave. To allow partners to have stands open to the public During the day of orientation, keep 2 hours to teach young people in phase of insertion how to write a good CV, and LM. Organize with the young people an appointment of simulation of job interview. | Labour market orientation, job hunting skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 | Young people | 64 | 4 | SOS, Express Toamasina | 429.56
Atsinanana | Company visit | Expose | Workplace visit | Conducting impregnation visits at partner institutions for 64 youth Visit companies, including DHL or establishments chosen according to the needs of the young people to help them confirm their choice but also to confront the reality according to the established job descriptions, to discover also the existing jobs in this field | Labour market orientaiton | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 | Young people | 64 | 4 | SOS, Express Toamasina | 560.62
Atsinanana | Career talk | Expose | Career talk | Conducting a career conference with young people who have achieved professional success for our young people, and producing job description booklets by DHL Volunteers partners and staff. We invite young people whose career path is positive and whose job is interesting to present and discuss their job (oral job description). If they can't come, ask them to make a power point video of their career path, so that the information received is direct, A job description made by DHL volunteers will be distributed. The volunteers will write in one or two pages their academic and professional background. To indicate the steps to follow to become like them. Explain the pathways, attitudes and profile, job market, salary range. | Labour market orientation, job hunting skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 - May 2023 | Young people | 64 | 4 | SOS, Express Toamasina
Atsinanana | Sharing workshop on the Logistics profession | Explore | Logistic-related training | Educate program participants on the world of logistics, including problem-solving and teamwork activities on the topic of logistics | Technical skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | Juin - Décembre | Young people | 64 | 4 | SOS, Express Toamasina | 253.07
Atsinanana | Language practice workshop | Explore | Employability skills training | organize days of language practice with the volunteers to Help young people to be comfortable in the various communications (job interview, reception, etc.) | Social skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | Suivant disponibilité jeunes et DHL | Young people | 64 | 4 | SOS, Express Toamasina
Atsinanana | Internship in the retail department | Practice | Internship | Young people are doing their internship at the retail department for learning about sales and communication skills while supporting the retail team | Work experience | yes | Face 2 face | Activité 1,3, 4, 7 | April 2023 - June 2023 | Young people | 2 | 2 | SOS, Express | 266.3884
TOTAL BUDGET MADAGASCAR | [13 empty] | 7444.8607

## Type of Activity
| # | Area | Activity | Description
Mandatory: 3 interventions per young person | 1 | Expose | Workplace visit | Visit of a local site or office (a few hours) to experience different places of employment where employees perform tasks, jobs and projects, including a career Q&A with DPDHL employees
| 2 | Expose | Career Fair | Stands are set up and each department inform about the variety of professional opportunities, as well as employees share their own work experience
| 3 | Expose | Career Talk | Employees talk about their occupations and how to access them including session on gender stereotypes or future of work
| 4 | Explore | Employability skills training | Train program participants in life skills and professional skills that prepare them for their first job or start their own business
| 5 | Explore | CV writing & interview skills training | Help young people to create an impactful CV and learn how to prepare for an interview
| 6 | Explore | Logistics-related training | Train program participants about the world of logistics, including logistics-themed problem solving and teamwork activities
| 7 | Explore | Job shadowing | On-the-job training (up to one week) that allows to observe an employee performing a job role, incl. the opportunity to ask questions throughout the day or at the end of the experience
| 8 | Explore | Mentoring | Support program participant to develop skills and attitudes needed to progress into employment, training or further education
Optional | 9 | Practice | Internship | Short-term working experience (up to six months) that integrates theory and skills learned in the classroom with practical application and skills development in a professional setting
| 10 | Practice | Apprenticeship | Provide temporary work experience including supervised on-the-job training, along with job-related skills training, all while earning a wage. Apprenticeship programs are full time positions within DPDHL
| 11 |  | Others
Intendes outcomes
Expose |  | Allow children and youth to obtain information about the professional work environment and provide an insight into career opportuntities and apprencticeships.
Explore |  | Young people actively explore the world of work, think about their future plans, lern specific skills to make important decisions about the future.
Practice |  | Provide youth with opportunities to experience the working world in a real business environment and to do a job that puts into practice the employability skills they have already developed.

## Action plan Madagascar ABE
Modèle de planification d'activité GoTeach - 2023
| Nom du pays: | Madagascar
| Nom du partenaire : | Partenaire SOS
| Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
ANTSIRABE | Introduction to employability | Explorer | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | Yes | Face 2 Face | Activity 1, 2, 3 | April 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 705.56
ANTSIRABE | Company discovery | Expose | Workplace visit | Visit to a local site or office (a few hours) to learn about different workplaces where employees perform tasks, jobs and projects, including a question-and-answer session with employees of the companies being visited. "Initiation of the Professional Workplace, including interest" | Labour Market orientation | Yes | Face 2 Face | Activity 1, 2, 3 | May 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 305.56
ANTSIRABE | How to write a CV and succeed in an interview. | Explorer | CV writing & interview skills training | Help youth create a powerful resume and learn how to prepare for an interview Understanding of the different methods of searching for job vacancies and how to apply resume and application letter writing skills and attend a job interview | Job hunting skills, technical skills | Yes | Face 2 Face | Activity 1, 2, 3 | May 2023 | Young people | 70 | 2 | SOS, DHL Agency Antsirabe | 407.78
total budget Antsirabe | [13 empty] | 1418.9

## Action plan Madagascar Anosy
Modèle de planification d'activité GoTeach - 2023
| Nom du pays: | Madagascar
| Nom du partenaire : | Partenaire SOS
| Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
Fort-Dauphin | Introduction to employability | Explorer | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | OUI | Présentiel | Activity 1, 2, 3 | April 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 705.56
Fort-Dauphin | Company discovery | Expose | Workplace visit | Visit to a local site or office (a few hours) to learn about different workplaces where employees perform tasks, jobs and projects, including a question-and-answer session with employees of the companies being visited. "Initiation of the Professional Workplace, including interest" | Labour Market orientation | OUI | Présentiel | Activity 1, 2, 3 | May 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 305.56
Fort-Dauphin | Know how to practice | Explore/Expose | Career talk / logistic-related training | Give young people an opportunity to discover promising professions according to their vision and choice Stimulate the creative spirit of young people through a presentation of professions by DHL volunteers on communication, IT and logistics. Not only will young people benefit from knowledge of the trades, but they will also discover the different production units in the sectors. | Labour Market orientation | OUI | Présentiel | Activity 1, 2, 3 | May 2023 | Young people | 50 | 2 | SOS, DHL Agency Anosy | 407.78
total budget Anosy | [13 empty] | 1418.9

## Action plan Madagascar Boeny
Modèle de planification d'activité GoTeach - 2023
| Nom du pays: | Madagascar
| Nom du partenaire : | SOS village d'enfants Madagascar
| Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
Boeny | Company and career discovery | Exposer | Company visit, career talk | Virtual visit of the workplace, meeting with staff by videoconference "Development of knowledge on educational and vocational guidance. Knowledge of the business world Knowledge of existing professions in the transport and logistics environment " | Labour market orientation | Yes | Virtual | 1,2,3 | 2023-07-01 | young people | 100 | 15 | SOS, Express | 422.2
Boeny | Professional meeting | Exposer | career talk | "Meeting with trade professionals to exchange and discuss their professional career on a trade (testimonial, sharing, success, etc.) and produce a catalog of existing professions at DHL Improve the career choice of young people according to their skills and talents. Young people have benchmarks in relation to their choice of orientation. Reinforced young people's understanding of the personal requirements of the world of professionalization With the catalog, young people develop skills in the concept of transport (air freight, rail, sea, etc.) and logistics | Labour market orientation | yes | Face 2 face | 1,2,3 | 2023-07-01 | young people | 100 | 1 | SOS, Express | 360.2
Boeny | How to write a CV and succeed in an interview, professionalisation | Explorer | CV writing & interview skills training | Employee training kit with DHL: CV development, cover letter, job application, interview "Young people master the conditions acquired upon hiring (CV writing, cover letter, attitude to the interview, etc.)" | Job hunting skills | yes | Face 2 face | 1,2,3 | 2023-07-01 | young people | 100 | 1 | SOS, Express | 452.2
total budget Boeny | [13 empty] | 1234.6

## Action plan Madagascar AMANGA
GoTeach Activity Planning Template - 2023
| Country name: | Madagascar
| Partner name: | Partenaire SOS
| Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
Analamanga | Activity 1: Career discovery, career talk | Expose | Career talk | Choice of professions/ choose the professions and train the participants by professional speakers (school and professional testimony/ choice of institutes/ duration and diplomas/ job market | Labour market orientation | Yes | Face 2 face | Activité 1,3,4 | April 2023 | Young people | 50 | 20 | SOS, Express | 591.11
Analamanga | Activity 2: Professional mentoring | Explore | Mentoring | Assist the program participant in developing the skills and attitudes necessary to progress to employment, training or further education | perosnal maturity, labour maket orientation | yes | Face 2 face | Activité 1,2,3,4 | June - November 2023 | Young people | 10 | 32 | SOS, Express | 37.33
Analamanga | Introduction to employability | Explore | Employability skills training | Train program participants in life and job skills that prepare them for their first job or to start their own business Understand what professions are in demand in the country and what are the requirements to be able to enter the different professions. Knowledge of various labor market programs and incentives for youth and how to apply or qualify. Find a match between your own skills and aspirations and market opportunities. | Labour maket orientation | yes | Face 2 face | Activité 1,3,4 | April 2023 | Young people | 50 | 20 | SOS, Express | 444.44
Analamanga | How to write a CV and succeed in an interview. | Explore | CV writing & interview skills training | Help youth create a powerful resume and learn how to prepare for an interview Understanding of the different methods of searching for job vacancies and how to apply resume and application letter writing skills and attend a job interview | Job hunting skills, technical skills | yes | Face 2 face | Activité 1,3, 4 | April 2023 | Young people | 50 | 20 | SOS, Express | 444.44
Analamanga | Internship in the retail department | Practice | Internship | Young people are doing their internship at the retail department for learning about sales and communication skills while supporting the retail team | Work experience | yes | Face 2 face | Activité 1,3, 4, 5 | April 2023 - June 2023 | Young people | 1 | 2 | SOS, Express | 133.1942
Analamanga | Job-shadowing retail department | Explore | Job-shadowing | Young people will learn the job as sales form the retail deparment during a week | Work experience | yes | Face 2 face | Activité 1,3, 4, 6 | April 2023 - June 2023 | Young people | 4 | 2 | SOS, Express | 44.3981
total budget Analamanga | [13 empty] | 1694.9123

## Action plan Madagascar Antsinan
Modèle de planification d'activité GoTeach - 2023
|  | Nom du pays: | Madagascar
|  | Nom du partenaire : | Partenaire SOS
|  | Activity Name | Area | Type of activity (Refer to Type of Activity Tab) | Activity description (Use the description in the Type of Activity Sheet) | Employability skills aimed for (Refer to Employability Skills Tab) Max 2 | Is this activity focused on Gender Equality (Yes/No) | Mode of Delivery (Vitual/Blended/Face 2 Face) | Activity set-up (activity 1, 2, 3; other activity) | When are you planning to implement the activity? (Start Month -Month End) | Group of participants (Students, Care co workers, young people, others) | # of GoTeach participants reached | # of volunteers involved | Who is preparing the activity (name & BU) | Estimated Activity cost (EUR)
1 | Atsinanana | Career discovery and employability training | Explore / Expose | Career fair and CV writing & interview skills training | Organize a day of orientation and training kits jobs Invite DHL, schools and professional institutions to present their available offers to the youth of SOS Village. To allow the youth to have ideas of orientation, to know the possibilities of course in Tamatave. To allow partners to have stands open to the public During the day of orientation, keep 2 hours to teach young people in phase of insertion how to write a good CV, and LM. Organize with the young people an appointment of simulation of job interview. | Labour market orientation, job hunting skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 | Young people | 64 | 4 | SOS, Express Toamasina | 429.56
2 | Atsinanana | Company visit | Expose | Workplace visit | Conducting impregnation visits at partner institutions for 64 youth Visit companies, including DHL or establishments chosen according to the needs of the young people to help them confirm their choice but also to confront the reality according to the established job descriptions, to discover also the existing jobs in this field | Labour market orientaiton | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 | Young people | 64 | 4 | SOS, Express Toamasina | 382.84
3 | Atsinanana | Career talk | Expose | Career talk | Conducting a career conference with young people who have achieved professional success for our young people, and producing job description booklets by DHL Volunteers partners and staff. We invite young people whose career path is positive and whose job is interesting to present and discuss their job (oral job description). If they can't come, ask them to make a power point video of their career path, so that the information received is direct, A job description made by DHL volunteers will be distributed. The volunteers will write in one or two pages their academic and professional background. To indicate the steps to follow to become like them. Explain the pathways, attitudes and profile, job market, salary range. | Labour market orientation, job hunting skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | April 2023 - May 2023 | Young people | 64 | 4 | SOS, Express Toamasina
4 | Atsinanana | Sharing workshop on the Logistics profession | Explore | Logistic-related training | Educate program participants on the world of logistics, including problem-solving and teamwork activities on the topic of logistics | Technical skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | Juin - Décembre | Young people | 64 | 4 | SOS, Express Toamasina | 253.07
6 | Atsinanana | Language practice workshop | Explore | Employability skills training | organize days of language practice with the volunteers to Help young people to be comfortable in the various communications (job interview, reception, etc.) | Social skills | yes | Face 2 face | Activité 1, 2, 3, 4, 5, 6 | Suivant disponibilité jeunes et DHL | Young people | 64 | 4 | SOS, Express Toamasina
7 | Atsinanana | Internship in the retail department | Practice | Internship | Young people are doing their internship at the retail department for learning about sales and communication skills while supporting the retail team | Work experience | yes | Face 2 face | Activité 1,3, 4, 7 | April 2023 - June 2023 | Young people | 2 | 2 | SOS, Express | 266.3884
| TOTAL | [13 empty] | 1331.8584